## WEBSITE QUESTIONS
QUESTIONS WORKSHEET
POST QUESTIONS AND ANSWERS ON SCHOOL ERATE WEBSITE PAGE
This worksheet is to assist school district in receiving and answering questions to post on their school website. Although any format can be used (i.E. User Blog, etc), this worksheet can be used as a template to post on school website
Please update and post weekly until DEADLINE for questions to be posted:
DATE (email received) | FROM (CONTACT) | SERVICE PROVIDER NAME | QUESTION | ANSWER (FROM SCHOOL DISTRICT) | DATE: ANSWERED | DATE: POSTED TO WEBSITE
2022-11-30 | Radu Prodan | BINYOD LLC | What is the longest/average length of the cable drops ? | Longest run ~250’ Average run ~125’ | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | What is the length of the fiber runs ? Is all the fiber indoor ? are there existing pathways ? | For the elementary locations fiber runs will be indoor only. At the high school there will be 4 indoor runs as well as 4 outdoor runs. Again all distances are estimates based on currently available information and could be subject to change. Fiber runs will range from 200’ to up to 500’. For internal fiber runs provisions will be made to have conduit in place with pull strings. Outdoor runs have no existing pathways as they will be new installations. | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | Will you accept partial proposals ? | No. | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | What brand are the SFP transceivers for ? | Network equipment vendor has yet to be chosen. All SFP modules should be at a minimum SFP+ and will vary depending on existing fiber installations on if they need to be single mode/multimode. | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | Are additional patch cords, panels required ? | This will be primarily for new construction will not have any existing patch panels or cords. | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | Are there existing racks in place or new racks are required too ? what kind ? | New construction will not have any existing racks. Racks should be sized accordingly with number of runs to that MDF/IDF. Racks should be wall mounted and have a locking front. | 2022-11-30 | 2022-11-30
2022-11-30 | Radu Prodan | BINYOD LLC | Can you share the plans if any ? | Most of the proposal is to provide cable and fiber runs in the new high school and new elementary school which is currently being designed. As we are just in the design phase, detailed architectural drawings are not available yet. However, we can provide a basic floorplan design for the two new buildings. | 2022-11-30 | 2022-11-30